## Project Info
<your logo>
Project Details
Customer | Duo | Duration | 10
Project |  | Start date
Customer contact |  | End date
Prepared by |  | Delivery | Onsite
Verison History
Version | Date | Prepared by | Description
0.1 Draft |  |  | Initial draft

## Week 1
Start Time | End Time | Session | Objectives | Mule Attendees | Client Attendees | Topics
Monday, Day 1 (Onsite)
10:00 | 11:00 | Kickoff | Review Goals and Objectives for the Engagement. Review Schedule for the week and confirm availability of Client resources. | Solution Architect, Engagement Manager, Account Executive | Sponsor (if applicable), Project Manager, Architects, Developers, Operations
11:00 | 12:30 | Current Application & Functional Review | Duo Demo/walk-through of current Client application and Services | Solution Architect | Client Architects | Current high Level Application Architecture Current State and High Level end state overview Current challenges
14:00 | 16:00 | High Level Architecture Review | Understand high level architecture, interfaces, environments,physical infrastructure setup and purposes | Solution Architect | Client Architects | Current high level Security Architecture Current high level Physical Architecture Discuss Application requirements
16:00 | 17:00 | Documentation and Next Steps | Review documentation, define next steps, and prepare for tomorrow. | Solution Architect
Tuesday, Day 2 (Onsite)
9:00 | 10:30 | Architecture: Physical Architecture Discussion | Discuss and Define Mule Configuration for Dev, Stage, Production - HA - Reliability - Non-functional requirements - Security requirements -Production Setup requirements | Solution Architect | Client Architects | Discuss Infrastructure and Network Architecture Discuss Security Requirements Authentication and Authorization Proposed Security, Application and Infrastructure Architecture
11:00 | 12:00 | Code Migration and Propagation Operations Monitoring Overivew | Discuss Code Deployment Processes - Use Cases - Tools - Best Practices - Define migration approaches, including pros/cons of each approach. | Solution Architect | Client Architects, Developers | Monitoring requirements (Currently we are using SCOM) Statistics and Logging requirements SDLC Unit Testing
12:00 | 13:00 | Lunch
14:00 | 17:00 | Setup QA/UAT Environment | Setup QA/UAT environment that adheres to the recommended practices | Solution Architect | Client Architects, Operations Team
Wednesday Day 3(Onsite)
9:00 | 12:00 | Detailed Solution Design Discussion | Define Core Mule Flows/Templates - Operations Define Applications and best practices Identify Common Connectors | Solution Architect | Client Architects, Developers | Backward Compatibility Error and exceptional Handling Using existing .Net Service HA & Clustering
12:00 | 13:00 | Lunch
13:00 | 17:00 | Infrastructure(continued) | TFs setup & configuration Jenkins setup | Solution Architect | Client Architects, Developers | Build Automation Continous Integration TFS & Jenkins setup
Thursday Day 4 (Onsite)
9:00 | 12:00 | Review Core use case 1 & 2: & Design Review changes to Core Applications | Define Core Mule Flows/Templates - Error Handling Define Applications and best practices Identify Common Connectors | Solution Architect | Client Architects, Developers
12:00 | 13:00 | Lunch
13:00 | 16:00 | Review Core use case 1 & 2: & Design Review changes to Core Applications | Define Core Mule Flows/Templates - Error Handling Define Applications and best practices Identify Common Connectors | Solution Architect | Client Architects, Operations Team | Performance & Capacity Planning Clustering Setup Infrastructure Recommendation & Validation
Friday Day 5 (Onsite)
9:00 | 13:00 | Q& A. Formalize Recommendation, Open Discussions, Follow ups | Formulate Integraton Services Blueprint Recommendations Review documentation, define next steps, and prepare for 2nd week | Solution Architect | Client Architects, Developers

## Week 2
Start Time | End Time | Session | Objectives | Mule Attendees | Client Attendees
Monday & Tuesday Day 6 & 7 (Onsite)
9:00 | 12:00 | Review Core Use cases 3 & Detailed design | Define Core Mule Flows/Templates - Operations Define Applications and best practices Identify Common Connectors | Solution Architect | Client Architects, Developers
12:00 | 13:00 | Lunch
13:00 | 17:00 | Review Core use case II: & Design Review changes to Core Applications | Define Core Mule Flows/Templates - Error Handling Define Applications and best practices Identify Common Connectors | Solution Architect | Client Architects, Developers
16:00 | 17:00 | Documentation and Next Steps | Review documentation, define next steps, and prepare for tomorrow. | Solution Architect
Wednesday, Day 8 (Onsite)
9:00 | 12:00 | Infrastructure(continued) | TFs setup & configuration Jenkins setup | Solution Architect | Client Architects, Developers | Build Automation Continous Integration TFS & Jenkins setup
12:00 | 13:00 | Lunch
13:00 | 17:00 | Solution Architecture Definition | Capture Architecture Recommendations. Do an Initial Review | Solution Architect | Client Architects, Developers
Thursday, Day 9 (Onsite)
TBD |  | Reserved
Friday Day 10 (Remote)
9:00 | 13:00 | Q& A. Formalize Recommendation, Open Discussions, Follow ups | Document Architecture Blueprint recommendations and next steps. Schedule a readout session on findings and plan | Solution Architect | Client Architects, Developers